## Q4 Tracker
Task | Tech Priority | Project | BRD Name | BRD Status | Task Details | Priority | Release | Efforts (PD) | Status | Owner | Test Scenarios Completion Date | Test cases Completion Date | Test Case Review status | %Dev | Dev Start Date | Dev End Date | QAT | Test case execution Date(QAT) | UAT Status | Tech Check out | QA Check out | User Check out | Questions | Answer | Comments
Sync up UAT from PROD |  | Drop Copy |  | Draft, Sent for Business review | Identify the servers in UAT 1. Identify the server which we are using in UAT 2. List down what server has what configuration. Document it against Prod server 3. Keep each configuration just like Prod | 1 | R1 |  | Closed | Yuvaraj |  |  |  | 100% |  | 2018-01-05 |  |  | Pending |  |  |  | Yog-01/08: Where is the server list. Yog-01/08: Jyoti is working on server configureation. ETA = Tuesday. Yog-01/08: Is everything in UAT same as that of prod ( software version and settings)
Sync up UAT from PROD |  | Drop Copy |  |  | Latest recon util code | 1 | R1 |  | Closed | Saurabh |  |  |  | 100% |  | 2018-01-05 |  |  | Pending |  |  |  | Yog-01/08: is the code build from latest code in github Yog-01/08: Is the branch / tag created
Sync up UAT from PROD |  | Drop Copy |  |  | Inform the team so that nobody changes anything in UAT | 1 | R1 |  | Closed | Yuvaraj |  |  |  | 100% |  | 2018-01-05 |  |  | Pending |  |  |  | Yog-01/08: Have we stopped touching the UAT server settings? Yog-01/08:We need to raise the entitlement to get dap. Yog-01/08:We need to un-install exceed from all developer machine. Yog-01/08:Who all have exceed. Need the list.
Sync up UAT from PROD |  | Drop Copy |  |  | Deploy the code in uat 1. Move QRK package and all related configuration for the FX Recon (2425982) from prod to UAT a. (/opt/rectify/recs/realtime/FASTMATCH_AGG-vs-FASTMATCH_GMA-QR2425982) b. topoly property unuder QRK config package c. RIO Topology /ETL/feeds d. Ask User to send messages- Yuvaraj e. Testing of this recon 2. Test it in UAT. it should be running fine 3. Change the latest reocn iteration jar and same recon should be running fine in UAT | 1 | R1 |  | Open | Saurabh |  |  |  | 80% |  | 2018-01-10 |  |  | Pending |  |  |  | Yog-01/08:Please update this task based on our team discussion today
Sync up UAT from PROD |  | Drop Copy |  |  | Ensure that every setting in UAT is in sync with that of prod | 1 | R1 |  | Open | Yuvaraj | [5 empty] | 2018-01-10 |  |  | Pending |  |  |  | Yog-01/08: How are we ensuring it.
Sync up UAT from PROD |  | Drop Copy |  |  | Function Testing on UAT | 1 | R1 |  | Open | Yuvaraj | [5 empty] | 2018-01-12 |  |  | Pending |  |  |  | Yog-01/08: Need the list of test cases
Sync up UAT from PROD |  | Drop Copy |  |  | Compare / Test to ensure that the code that is running in Prod is in synch with github | 1 | R1 |  | Open | [6 empty] | 2018-01-10 |  |  | Pending
Sync up UAT from PROD |  | Drop Copy |  |  | Check the last update dates of files in Prod | 1 | R1 |  | Open | Saurabh | [5 empty] | 2018-01-10 |  |  | Pending |  |  |  | Yog-01/08: Need to start this task tomorrow
Sync up UAT from PROD |  | Drop Copy |  |  | Check that last CMP’s used for deployment | 1 | R1 |  | Open | Saurabh | [5 empty] | 2018-01-10 |  |  | Pending |  |  |  | Yog-01/08: Need to start this task tomorrow
Sync up UAT from PROD |  | Drop Copy |  |  | Backup plan | 1 | R1 |  | Open | Yuvaraj | [5 empty] | 2018-01-10 |  |  | Pending |  |  |  | Yog-01/08: It should be part of deployment plan/ document
Sync up UAT from PROD |  | Drop Copy |  |  | UAT test plan / test cases – server down testing | 1 | R1 |  | Open | Yuvaraj | [5 empty] | 2018-01-10 |  |  | Pending |  |  |  | Do we need this as part of R1?
Hazelcast - Enhancements |  | Drop Copy |  |  | Upgrade the version of Hazelcast | 1 | R2 | 3 | Open | Vinayak |  |  |  | 50% | 2018-01-08 | 2018-01-10 |  |  | Pending |  |  |  | Yog-01/08: Mention the version
Hazelcast - Enhancements |  | Drop Copy |  |  | Figure out what additional things are offered by new version that can be considered for Realtime Framework | 2 | R2 |  | Open | [9 empty] | Pending
Hazelcast - Enhancements |  | Drop Copy |  |  | Mancenter should capture missing stats of hazelcast nodes and for all Hash | 1 | R2 | 1 | Open | Vinayak |  |  |  | 50% | 2018-01-08 | 2018-01-08 |  |  | Pending
Hazelcast - Enhancements |  | Drop Copy |  |  | Mancentre for archival data | 1 | R2 | 1 | Open | Vinayak |  |  |  | 50% | 2018-01-08 | 2018-01-08 |  |  | Pending
Hazelcast - Enhancements |  | Drop Copy |  |  | Try out different Serialization and publish the stats and decide on the seariliaztion to be used. | 1 | R2 | 2 | Open | Ramkumar |  |  |  |  | 2018-01-11 | 2018-01-12 |  |  | Pending |  |  |  | Yog-01/08: Provide the list of seariazations to be considered. Yog-01/08: How to measure the performance of each serialization
Hazelcast - Enhancements |  | Drop Copy |  |  | Add Additional Nodes to Hazelcast cluster | 1 | R2 | 2 | Open | Vinayak
Hazelcast - Enhancements |  | Drop Copy |  |  | Configure the backup strategy | 1 | R2 | 2 | Open | Vinayak
Hazelcast - Enhancements |  | Drop Copy |  |  | Analyze the partitions in Hazelcast | 1 | R2 | 2 | Open | Vinayak
Hazelcast - Enhancements |  |  |  |  | Licence version of Hazelcast | 2 | R2 | 2 | Open | Vinayak
Garbage collection |  | Drop Copy |  |  | List down the Heap settings acorss all the apps running on different servers | 1 | R2 | 5 | Open | Ramkumar |  |  |  |  | 2018-01-08 | 2018-01-12 |  |  | Pending
Garbage collection |  | Drop Copy |  |  | Generate GC logs for hazelcast | 1 | R2 |  | Open | [9 empty] | Pending
Garbage collection |  | Drop Copy |  |  | Analyze the GC for Hazelcast | 1 | R2 |  | Open | [9 empty] | Pending
Enhance logging to track issues |  | Drop Copy |  |  | Add thread id, hostname in the log | 1 | R2 | 1 | Open | Pravin |  |  |  | 90% | 2018-01-08 | 2018-01-08 |  |  | Pending
Enhance logging to track issues |  | Drop Copy |  |  | Check if anywhere exception is being consumed. We need to log the exception with message details. | 1 | R2 | 2 | Open | Pravin |  |  |  | 50% | 2018-01-08 | 2018-01-09 |  |  | Pending |  |  |  | Yog-01/08:
Log Capture |  | Drop Copy |  |  | 1.Log to be pushed to kafka and then to Elasticsearch 2. Check if it the above change does not create any performance issue. 3. If the above change works, then we can add more logging to the code to capture the issues 4.More analysis to be done to come up with a final approach for better logging | 1 | R2 | 5 | Open | Dhanunjay |  |  |  |  | 2018-01-08 | 2018-01-12 |  |  | Pending |  |  |  | Yog-01/08:
Kafka - Enhancements |  | Drop Copy |  |  | Kafka Version Upgrade | 2 | R3 | 2 | Open | Vinayak | [8 empty] | Pending
Kafka - Enhancements |  | Drop Copy |  |  | Figure out what additional things are offered by new version that can be considered for Realtime Framework | 2 | R3 | 1 | Open | Vinayak |  |  |  |  | 2018-01-08 | 2018-01-08 |  |  | Pending
Kafka - Enhancements |  |  |  |  | Kafka fix proposed by Yuvaraj | 2 | R4 | 2 | Open | Yuvaraj | [8 empty] | Pending |  |  |  | Yog-01/08: Cannot be done along with Kafka version upgrade
Storm - Enhancements |  | Drop Copy |  |  | Storm Version Upgrade | 3 | R4 | 2 | Open | Vinayak | [8 empty] | Pending
Storm - Enhancements |  | Drop Copy |  |  | Figure out what additional things are offered by new version that can be considered for Realtime Framework | 3 | R4 | 1 | Open | Vinayak |  |  |  |  | 2018-01-08 | 2018-01-08 |  |  | Pending
Storm - Enhancements |  |  |  |  | Back Pressure settings for Storm | 1 | R4 | 2 | Open | Vinayak | [8 empty] | Pending
Load Testing |  |  |  |  | Capacity Planning | 1 | R1 |  | Open | [9 empty] | Pending
Load Testing |  |  |  |  | Simulating the load and confirming it using Kafka Manager | 1 | R2 | 1 | Open | Tharun
Load Testing |  |  |  |  | Test by filtering the messages
Environment Setup |  |  |  |  | EMEA | 2 | R1 |  | Open | [9 empty] | Pending
Environment Setup |  |  |  |  | APAC | 2 | R1 |  | Open | [9 empty] | Pending
Environment Setup |  |  |  |  | Performance | 2 | R1 |  | Open | [9 empty] | Pending
Environment Setup |  |  |  |  | Dev | 2 | R1 |  | Open | [9 empty] | Pending
Recon Onboarding |  |  |  |  | Recon Onboarding process finalization | 2 | R1 |  | Open | [9 empty] | Pending
Support |  |  |  |  | Bring up Production Support team | 2 | R2 |  | Open | [9 empty] | Pending
Support |  |  |  |  | Monitoring by Support Resource | 1 |  |  | Open | [9 empty] | Pending
Reports |  |  |  |  | Reports using Apache Zeppelin | 1 |  | 1 | Open | Tharun |  |  |  |  | 2018-01-19 | 2018-01-19 |  |  | Pending |  |  |  | Yog-01/08: What is this item?
Source Duplicate Check |  |  |  |  | Analysis to find unique indentity from Message | 1 | R3 | 3 | Open | [5 empty] | 2018-01-09 | 2018-01-11 |  |  | Pending |  |  |  | Yog-01/08:
Source Duplicate Check |  |  |  |  | Aproach finalization | 1 | R3 | 1 | Open | Vinayak |  |  |  |  | 2018-01-15 | 2018-01-15 |  |  | Pending |  |  |  | Yog-01/08:
Source Duplicate Check |  |  |  |  | Implementing duplicate checks | 1 | R3 | 3 | Open | Vinayak |  |  |  |  | 2018-01-16 | 2018-01-18 |  |  | Pending |  |  |  | Yog-01/08:
Source Duplicate Check |  |  |  |  | Insert source duplicate message in a new kafka topic | 1 | R3 | 1 | Open | Vinayak |  |  |  |  | 2018-01-19 | 2018-01-19 |  |  | Pending |  |  |  | Yog-01/08:
Source Duplicate Check |  |  |  |  | Pull source duplicate from Kafka to Elasticsearch using Logstash | 1 | R3 | 2 | Open | Dhanunjay |  |  |  |  | 2018-01-15 | 2018-01-16 |  |  | Pending |  |  |  | Yog-01/08:
Source Duplicate Check |  |  |  |  | Show source duplicates in Kibana | 1 | R3 | 3 | Open | Dhanunjay |  |  |  |  | 2018-01-17 | 2018-01-19 |  |  | Pending |  |  |  | Yog-01/08:
Output Duplicate Check |  |  |  |  | Analysis Duplicate checks | 1 | R3 | 2 | Open | Yuvaraj |  |  |  |  | 2018-01-12 | 2018-01-15 |  |  | Pending |  |  |  | Yog-01/08:
Output Duplicate Check |  |  |  |  | Implementation for duplicate checks | 1 | R3 | 3 | Open | Vinayak |  |  |  |  | 2018-01-16 | 2018-01-18 |  |  | Pending |  |  |  | Yog-01/08:
Output Duplicate Check |  |  |  |  | Define schema for storing matching result | 1 | R3 | 1 | Open | Vinayak |  |  |  |  | 2018-01-17 | 2018-01-17 |  |  | Pending |  |  |  | Yog-01/08:
Output Duplicate Check |  |  |  |  | Save output of matching bolt to Cassandra | 1 | R3 | 2 | Open | Vinayak |  |  |  |  | 2018-01-18 | 2018-01-19 |  |  | Pending |  |  |  | Yog-01/08:
Performance Monitoring |  | Drop Copy |  |  | Wily Introscope | 1 | R1 | 5 | Open | Ramkumar |  |  |  |  | 2018-01-15 | 2018-01-19 |  |  | Pending |  |  |  | Yog-01/08:
Performance Monitoring |  | Drop Copy |  |  | StatsD Client | 1 | R1 | 5 | Open | Jyoti |  |  |  |  | 2018-01-15 | 2018-01-19 |  |  | Pending |  |  |  | Yog-01/08:
Performance Monitoring |  | Drop Copy |  |  | StatsD Server | 1 | R1 | 2 | Open | Dhanunjay |  |  |  |  | 2018-01-22 | 2018-01-23 |  |  | Pending |  |  |  | Yog-01/08:
Performance Monitoring |  | Drop Copy |  |  | Beats Setup | 1 | R1 | 2 | Open | Dhanunjay |  |  |  |  | 2018-01-24 | 2018-01-25 |  |  | Pending |  |  |  | Yog-01/08:
Incremental Break Processing |  |  |  |  | Reading from Kafka message break topic | 1 | R3 | 1 | Open | Ramkumar |  |  |  |  | 2018-01-22 | 2018-01-22 |  |  | Pending |  |  |  | Yog-01/08:
Incremental Break Processing |  |  |  |  | Feeding these messages to matching bolt | 1 | R3 | 1 | Open | Ramkumar |  |  |  |  | 2018-01-23 | 2018-01-23 |  |  | Pending |  |  |  | Yog-01/08:
Incremental Break Processing |  |  |  |  | Incremental Job - Understand this job. Test this job. - Does this job work for Accumulate | 2 | R3 | 2 | Open | Yuvaraj
Real Time Dashboard |  |  |  |  | Analysis of Real Time Dashbpard | 1 | R4 |  | Open | [9 empty] | Pending |  |  |  | Yog-01/08:
Real Time Dashboard |  |  |  |  | Pull data from kafka topic to Elasticsearch | 1 | R4 | 2 | Open | Yuvaraj |  |  |  |  | 2018-01-22 | 2018-01-23 |  |  | Pending |  |  |  | Yog-01/08:
Real Time Dashboard |  |  |  |  | Build dashboard on kibana | 1 | R4 | 1 | Open | Guru |  |  |  |  | 2018-01-24 | 2018-01-24 |  |  | Pending |  |  |  | Yog-01/08:
Real Time Dashboard |  |  |  |  | Integrate Kibana into Portal | 1 | R4 | 1 | Open | Guru |  |  |  |  | 2018-01-25 | 2018-01-25 |  |  | Pending |  |  |  | Yog-01/08:
New Recon Onboarding |  |  |  |  | Analysis for recon onboarding | 2 |  | 3 | Open | Deepak |  |  |  |  | 2018-01-29 | 2018-01-31 |  |  | Pending |  |  |  | Yog-01/08:
New Recon Onboarding |  |  |  |  | Recon Deployment on UAT | 2 |  | 2 | Open | Guru |  |  |  |  | 2018-02-01 | 2018-02-02 |  |  | Pending |  |  |  | Yog-01/08:
New Recon Onboarding |  |  |  |  | Recon Testing | 2 |  | 2 | Open | Dhanunjay |  |  |  |  | 2018-02-01 | 2018-02-02 |  |  | Pending |  |  |  | Yog-01/08:
New Recon Onboarding |  |  |  |  | Any new Real time recon - Will it be Accumulte or incremental. | 1 | R1 |  | Open
New Recon Onboarding |  |  |  |  | Accumulate type it should not populate the SID in Recon Portal | 2 |  |  | Open | Yogendra
Backout Plan |  |  |  |  | Create Backout plan. Backout Test cases | 1 |  | 2 | Open | Saurabh |  |  |  |  | 2018-02-02 | 2018-02-03 |  |  | Pending |  |  |  | Yog-01/08:
Backout Plan |  |  |  |  | Execute Backout plan | 3 |  | 3 | Open | Yuvaraj |  |  |  |  | 2018-01-29 | 2018-01-31 |  |  | Pending |  |  |  | Yog-01/08:
Alerts generation in the provided format | [5 empty] | 5 | Future | [11 empty] | Pending
System Duplicates |  |  |  |  | Do we need to restart the topology every week. Need to check? | 1 | R1 | 1 | Open | Saurabh
System Duplicates |  |  |  |  | Figure out a pattern in which system duplicates are generate. Repeat it. | 1 | R1 | 1 | Open | Saurabh
System Duplicates |  |  |  |  | Talk to Yashwanth | 1 | R1 | 1 | Open | Saurabh
System Duplicates |  |  |  |  | Confirm the duplicates on the zookeeper commit points. Check the output files. Check the portal db | 1 | R1 | 1 | Open | Saurabh
Others |  |  |  |  | Develop Breaks threshold for the Realtime Recon processing | 2 | R3 | 1 | Open | Yogendra
Recon Portal |  |  |  |  | Portal should not read matches based on a configurable setting | 2 | R1 | 1 | Open | Yogendra
Others |  |  |  |  | Separation of the Transforamtion topology | 5 | R5 | 2 | Open | Vinayak
Others |  |  |  |  | Identify the failure scenarios during development and testing | 4 | R1 | 1 | Open | Vinayak
Hazelcast - Enhancements |  |  |  |  | Do we lose messges when hazelcast is restarted | 3 | R1 | 1 | Open | Vinayak
Zookeeper |  |  |  |  | Upgrate the version of zookeeper | 3 | R3 | 1 | Open | Vinayak
Zookeeper |  |  |  |  | Separate cluster for kafka and storm | 3 | R3 | 1 | Open | Vinayak
ELK |  |  |  |  | upgrade the version | 4 | R4 | 1 | Open | Vinayak
Recon Portal |  |  |  |  | Option for Recall of matched item from Portal | 4 | R1 | 1 | Open | Yogendra
Recon Portal |  |  |  |  | Turn Off loading of Match items in Reconportal | 1 | R1 | 1 | Open | Yogendra
Java 9 |  |  |  |  | upgrade to java 9 | 4 | R4 | 1 | Open | Vinayak
Others |  |  |  |  | Move the configuration and artifact of UAT and PROD to github | 1 | R1 | 1 | Open | Yuvaraj
User Testing |  |  |  |  | Exit criteria for the existing production recon | 1 | R1 | 1 | Open | Arkady
Storm - Enhancements |  |  |  |  | 1. Add HazelCast Event listener handler method in ExecuterService | 1 |  | 2 | Open | Vinayak
Storm - Enhancements |  |  |  |  | 2. Revisit Kafka Spout implementation to support storm back pressure | 1 |  | 2 | Open | Vinayak
Formulas:
Dev End Date = [Dev Start Date]+[Efforts (PD)]-1
Dev End Date = [Dev Start Date]+2+[Efforts (PD)]-1

## Resource Allocation
Resources | time axis 2018-01-05 to 2018-04-04
Vinayak | 2018-01-05: A17; 2018-01-08: A17; 2018-01-09: A17; 2018-01-10: A17; 2018-01-11: A34; 2018-01-12: A34
Pravin | 2018-01-05: A22; 2018-01-08: A22; 2018-01-09: A22; 2018-01-10: A22; 2018-01-11: A26; 2018-01-12: A26; 2018-01-15: A38; 2018-01-16: A38; 2018-01-17: A38
Dhanunjay | 2018-01-05: A23; 2018-01-08: A23; 2018-01-09: A23; 2018-01-10: A23; 2018-01-11: A25; 2018-01-12: A25; 2018-01-15: A37; 2018-01-16: A37; 2018-01-17: A37
Tharun | bar: 2018-01-05; 2018-01-08 to 2018-01-09; 2018-01-11 to 2018-01-12
Saurabh | 2018-01-05: x; 2018-01-08: X; 2018-01-09: x; 2018-01-10: x; 2018-01-11: A26; 2018-01-12: A27
Ramkumar | bar: 2018-01-05; 2018-01-08 to 2018-01-12
Yuvaraj | 2018-01-05: x; 2018-01-08: A33; 2018-01-09: A33; 2018-01-10: A33; 2018-01-11: x; 2018-01-12: x
Jyoti | 2018-01-05: A28; 2018-01-08: A28; 2018-01-09: A28; 2018-01-10: A28
Deepak
Yogendra
Arkady

## Lookup (hidden)
Status | UAT Status
Open | Pending
Closed | Deployed
Success